## Team
Initials | First | Last | Email | GitHub Username
ZL | Zhi | Li | zli69@stevens.edu | jackyli0318
YZ | Yu | Zhang | yzhan91@stevens.edu | ZhangYuu
YZ | Yujie | Zhong | yzhong5@stevens.edu | iamme1234567
|  |  | GitHub Repository: | https://github.com/jackyli0318/SSW-555.git

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | Yu | Done
1 | US02 | Birth before marriage | Yu | Done
1 | US22 | Unique IDs | Zhi | Done
1 | US27 | Include individual ages | Zhi | Done
1 | US09 | Birth before death of parents | Yujie | Done
1 | US21 | Correct gender for role | Yujie | Done
2 | US04 | Marriage before divorce | Zhi | Done
2 | US40 | Include input line numbers | Zhi | Done
2 | US07 | Less then 150 years old | Yu | Done
2 | US06 | Divorce before death | Yu | Done
2 | US23 | Unique name and birth date | Yujie | Done
2 | US17 | No marriage to descendants | Yujie | Done
3 | US03 | Birth before death | Yu | Done
3 | US05 | Marriage before death | Yu | Done
3 | US30 | List living married | Zhi | Done
3 | US31 | List living single | Zhi | Done
3 | US29 | List deceased | Yujie | Done
3 | US37 | List recent birth | Yujie | Done
4 | US10 | Marriage after 14 | Yu | Done
4 | US42 | Reject illegitimate dates | Yu | Done
4 | US18 | Siblings should not marry | Zhi | Done
4 | US20 | Aunts and uncles | Zhi | Done
4 | US14 | Multiple births <= 5 | Yujie | Done
4 | US13 | Siblings spacing | Yujie | Done

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2018-02-11 | 24 |  | 0
Sprint 1 | 2018-02-26 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2018-03-19 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2018-04-02 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2018-04-23 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2018-02-11 | 24 |  | 0
2018-02-26 | 18 | 6 | 128 | 195 | 39.3846
2018-03-19 | 12 | 6 | 217 | 100 | 53.4
2018-04-02 | 6 | 6 | 314 | 100 | 58.2
2018-04-16 | 0 | 6 | 423 | 109 | 60

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Review Results
US01 | Dates before current date | ZY | Done | 30 | 25 | 35 | 30 | Yes
Keep doing:
T01.01 | Store current date | ZY | [6 empty] | Determine and unite the standard input and output formats firstly
T01.02 | Store dates | ZY | [6 empty] | If coming across some problem, ask for help would be fine.
T01.03 | Compare dates and current date | ZY | [6 empty] | Pair programming
Avoid:
US02 | Birth before marriage | ZY | Done | 40 | 30 | 20 | 20 | Yes | Changing others code without telling them and making marks on the code.
T02.01 | Store Birth(both 2 people) | ZY
T02.02 | Store marriage date | ZY
T02.03 | Compare marriage date to birth | ZY
US09 | Birth before death of parents | Yujie | Done | 130 | 70 | 36 | 60 | Yes
T09.01 | Store birth date | Yujie
T09.02 | Store death date of parents | Yujie
T09.03 | Compare dates | Yujie
US21 | Current gender for role | Yujie | Done | 90 | 50 | 8 | 5 | Yes
T21.01 | Store gender | Yujie
T21.02 | Correct gender for each role | Yujie
US22 | Unique IDs | Zhi | Done | 30 | 20 | 12 | 30 | Yes
T22.01 | Store ID in a set | Zhi
T22.02 | Judge whether the ID is in the set | Zhi
T22.03 | If existed, return false. If not existed, return true. | Zhi
US27 | Include individual ages | Zhi | Done | 40 | 30 | 44 | 50 | Yes
T27.01 | Calculate the date between the birthday and the present date | Zhi
T27.02 | Display the result as the age | Zhi

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Review Results
US23 | Unique name and birth date | Yujie | Done | 40 | 30 | 11 | 8 | Yes
Keep doing:
T23.01 | Store names and birthdates | Yujie | [6 empty] | Continue using the designed standard input and output format.
T23.02 | Compare names and birthdates | Yujie | [6 empty] | Solving problem together. Face-to-face meeting would be better.
T23.03 | Discard duplicated individuals | Yujie | [6 empty] | Pair programming
Keep anouncing in group chat when the project gets changed.
US17 | No marriage to descendants | Yujie | Done | 20 | 20 | 17 | 30 | Yes | Doing integration during the face-to-face meeting.
Review meeting after the sprint
T17.01 | Store parents ID and childrens ID | Yujie | [6 empty] | Planning meeting before the sprint
T17.02 | Check if parentsID in childrensID | Yujie
T17.03 | Return True or False | Yujie | [6 empty] | Avoid:
Changing others code without telling them and making marks on the code.
US07 | Less then 150 years old | ZY | Done | 20 | 20 | 4 | 5 | Yes | Doing integration on one's own.
T07.01 | get current age | ZY
T07.02 | compare current age with 150 | ZY
T07.03 | Return compare result | ZY
US06 | Divorce before death | ZY | Done | 20 | 20 | 22 | 25 | Yes
T06.01 | get divorce date
T06.02 | get death date
T06.03 | Compare divorce date & death date
T06.04 | Return compare result
US04 | Marriage before divorce | Zhi | Done | 20 | 20 | 15 | 20 | Yes
T04.01 | get the marriage date
T04.02 | get the divorce date
T04.03 | compare these two dates
T04.04 | return a bool
US40 | Include input line numbers | Zhi | Done | 20 | 20 | 20 | 30 | Yes
T40.01 | set a cnt for line counting
T40.02 | add 1 when a line is read
T40.03 | print the line number

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Review Results
US29 | List deceased | Yujie | Done | 10 | 5 | 6 | 5 | Yes
Keep doing:
T29.01 | Find deceased people in individual record | Yujie | [6 empty] | Using the designed standard input and output format.
T29.02 | Store them into a list | Yujie | [6 empty] | In person meeting.
Pair programming
US37 | List recent birth | Yujie | Done | 10 | 5 | 7 | 5 | Yes | Keep announcing in group chat when the project gets changed.
Doing integration after the meeting.
T37.01 | Find recent birth people in individual dictionary | Yujie | [6 empty] | Review meeting after the sprint.
T37.02 | Store them into a list | Yujie | [6 empty] | Planning meeting before the sprint
Avoid:
US30 | List living married | Zhi | Done | 10 | 15 | 15 | 20 | Yes | Holding a long meeting over the timebox.
T30.01 | read the family dictionary | [7 empty] | Changing others code without telling them and making marks on the code.
T30.02 | get all individuals in non-divorce family | [7 empty] | Doing integration on one's own.
T30.03 | check whether the individual is alive
T30.04 | if yes, add the individual in the list
T30.05 | print the list
US31 | List living single | Zhi | Done | 10 | 15 | 15 | 15 | Yes
T3101 | read the family dictionary
T3102 | get all individuals in non-divorce family and store them in a "married" list
T3103 | iterate the individual dictionary
T3104 | if the individual is not in the list and is older than 30, add the individual in the "single" list
T3105 | print the "single" list
US03 | Birth before death | ZY | Done | 15 | 10 | 26 | 30 | Yes
T03.01 | get deathdate
T03.02 | Get brithdate
T03.03 | make comparison
T03.04 | return result
US05 | Marriage before death | ZY | Done | 20 | 20 | 28 | 25 | Yes
T05.01 | get marry date
T05.02 | get husband death date
T05.03 | get wife death date
T05.04 | make comparison
T05.05 | return result

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Review Results
US10 | Marriage after 14 | ZY | Done | 10 | 15 | 8 | 10 | Done
T10.01 | get marriage date | [7 empty] | Keep doing:
T10.02 | get birth date | [7 empty] | Reuse user story code and reduce redundant work
T10.03 | count marriage age | [7 empty] | Keep adding comments with US number and descriptions.
T10.04 | return result | [7 empty] | Keep doing unit test before submitting the code.
Keep the standard input and output format.
US42 | Reject illegitimate dates | ZY | Done | 10 | 10 | 30 | 25 | Done | In-person meeting.
T42.01 | get date | [7 empty] | Pair programming
T42.02 | check date | [7 empty] | Keep announcing in group chat when the project gets changed.
T42.03 | return result | [7 empty] | Doing integration after the meeting.
Review meeting after the sprint.
US18 | Siblings should not marry | Zhi | Done | 20 | 30 | 16 | 25 | Done | Planning meeting before the sprint
T18.01 | Get the siblings list
T18.02 | Iterate the list and the family dict | [7 empty] | Avoid:
T18.03 | If both husband and wife are in the sibling list, print error
Holding a long meeting over the timebox.
US20 | Aunts and uncles | Zhi | Done | 20 | 30 | 25 | 35 | Done | Changing others code without telling them and making marks on the code.
T20.01 | Get the nieces and nephews list | [7 empty] | Doing integration on one's own.
T20.02 | Iterate the list
T20.03 | If the spouse is in the list, print error
US14 | Multiple births <= 5 | Yujie | Done | 25 | 20 | 16 | 30 | Done
US13 | Siblings spacing | Yujie | Done | 30 | 25 | 14 | 30 | Done

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)